## feature.csv
Name | InvestmentCategory | Project | Owner | Parent | Release | PlannedStartDate | PlannedEndDate | Description | DisplayColor | Notes | Ready | RiskScore | ValueScore | PreliminaryEstimate | State | listing_order | dataset | timecriticality | rroevalue | jobsize | RefinedEstimate
Shopping Cart | Cost Savings | Shopping Team | peter@acme.com | Minimal online shopping site | R1 | 2017-11-20 | 2017-12-15 | <p class="rally-rte-class-03cb47fb2"><span class="rally-rte-class-04dd18d0f">Build a shopping cart module to select items for eventual purchase. Provide basic navigation and shopping cart capabilities to mark items for purchase. Upon checkout, the Online Store will calculate a total for the order, including shipping and handling charges and the associated taxes, as applicable.&nbsp; The following payment options should be provided:</span></p><p class="rally-rte-class-03221dadb"><span class="rally-rte-class-0b1c8cea2"><img src="https://lh5.googleusercontent.com/R-2ZX8gA5GTrG8A2OzIRpBjUFx6_RNRSVoZQxOvo7gSmeP4Wjp6eIkWdOcv0s05-zf6Hm_L4OEfJLpvmjqiEUdC_b-bW-Xo9JkCqTFdYywCJvEueazAj3EfDrTxXUdGCpcAQeHM" width="500px;" height="138px;" class="CToWUd rally-rte-class-047830fe9" /></span></p><p class="rally-rte-class-03cb47fb2">High-level functionality is expected to include:</p><ul><li>Intake items from the Online Store Search &amp; Browse functions</li><li>Viewing Recent Purchases to encourage repeat purchases</li><li>Persisting the Shopping Cart content between sessions</li><li>Clear calls to action for Purchasing Items</li><li>Reasonable scalability for initial roll-out and early growth (TBD)</li></ul> | #105cab |  | FALSE | 3 | 8 | M | Develop | 1 | Test |  |  |  | 50
Support write API | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R1 | 2017-11-08 | 2017-12-12 |  | #4a1d7e |  | FALSE | 2 | 0 | S | Develop | 2 | Test |  |  |  | 30
Extended Email-to-case integration | Cost Savings | API Team | aaron@acme.com | Minimal online shopping site | R1 | 2017-11-11 | 2017-12-18 |  | #105cab |  | FALSE | 12 | 4 | M | Develop | 3 | Test |  |  |  | 50
Saving profile | Maintenance | Shopping Team | peter@acme.com | Personalized online shopping experience | R1 | 2017-11-11 | 2017-11-30 |  | #107c1e |  | FALSE | 2 | 0 | M | Develop | 4 | Test |  |  |  | 50
Online chat support | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R1 | 2017-11-08 | 2017-12-18 |  | #4a1d7e |  | FALSE | 5 | 3 | M | Develop | 5 | Test |  |  |  | 50
Purchase single product | Short Term Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R1 | 2017-11-05 | 2017-12-15 |  | #105cab |  | FALSE | 13 | 10 | M | Open Beta | 6 | Test |  |  |  | 50
Knowledgebase | Short Term Growth | Fulfillment Team | pam@acme.com | Integrate into Facebook as Knowledge base | R1 | 2017-11-14 | 2017-12-12 |  | #fce205 |  | FALSE | 6 | 1 | L | Done | 7 | Test |  |  |  | 80
Homepage | Cost Savings | Payment Team | peter@acme.com | Integrate in-store and online experience | R1 | 2017-12-05 | 2017-12-30 |  | #f9a814 |  | FALSE | 5 | 7 | L | Internal Release | 8 | Test |  |  |  | 80
Product purchase confirmation | Strategic Growth | Payment Team | peter@acme.com | Minimal online shopping site | R1 | 2017-11-11 | 2017-12-21 |  | #105cab |  | FALSE | 4 | 3 | S | Done | 9 | Test |  |  |  | 30
Returned shipments | Strategic Growth | Fulfillment Team | pam@acme.com | Integrate in-store and online experience | R1 | 2017-11-11 | 2017-12-21 |  | #f9a814 |  | FALSE | 5 | 5 | S | Develop | 10 | Test |  |  |  | 30
Search for products | Short Term Growth | Payment Team | peter@acme.com | Minimal online shopping site | R1 | 2017-11-29 | 2017-12-12 |  | #105cab |  | FALSE | 0 | 5 | XS | Open Beta | 11 | Test |  |  |  | 10
Archive packing slips | Strategic Growth | Fulfillment Team | pam@acme.com | Personalized online shopping experience | R1 | 2017-11-11 | 2017-12-21 |  | #107c1e |  | FALSE | 3 | 4 | S | Done | 12 | Test |  |  |  | 30
Order Status 2.0 | Strategic Growth | Payment Team | peter@acme.com | Modernize customer service portal | R1 | 2017-11-11 | 2017-12-15 |  | #4a1d7e |  | FALSE | 4 | 7 | M | Develop | 13 | Test |  |  |  | 50
Shopping history | Strategic Growth | Fulfillment Team | pam@acme.com | Personalized online shopping experience | R1 | 2017-11-05 | 2017-12-27 |  | #107c1e |  | FALSE | 4 | 0 | L | Develop | 14 | Test |  |  |  | 80
#ERROR! | None | Consumer Site | [13 empty] | 15 | Test
Realtime notifications | Strategic Growth | API Team | aaron@acme.com | Integrate social into shopping experience |  | 2018-02-03 | 2018-02-24 | All users should be able to easily login, logout, and safely store their relevant information with us<br /><br />Acceptance Criteria <ul> <li>Login requires username in email format and password</li> <li>One-click logout</li> <li>Logout provides link to login again</li> <li><b>Non-functional: https data transfer</b></li> <li><b>Non-functional: passwords stored encrypted in database</b></li> </ul> | #848689 |  | FALSE | 6 | 20 | L | Develop | 16 | Test
Email-to-case integration | Cost Savings | API Team | aaron@acme.com | Maintain legacy purchasing system | R2 | 2017-12-31 | 2018-02-24 |  | #df1a7b |  | FALSE | 1 | 9 | M | Develop | 17 | Test
Outbound SMS messages for support case updates | Cost Savings | API Team | aaron@acme.com | Maintain legacy purchasing system |  | 2018-01-09 | 2018-01-25 |  | #df1a7b |  | FALSE | 3 | 5 | M | Develop | 18 | Test
Credit card payments | Cost Savings | Payment Team | patricia@acme.com | Integrate in-store and online experience | R2 | 2018-01-09 | 2018-02-15 | see business case attached | #f9a814 |  | FALSE | 3 | 6 | L | Validate | 19 | Test
Purchase path | Cost Savings | Shopping Team | peter@acme.com | Re-build primary web app leverage API technology | R2 | 2017-12-31 | 2018-02-18 | <p class="rally-rte-class-03cb47fb2"><span class="rally-rte-class-04dd18d0f">Build a shopping cart module to select items for eventual purchase. Provide basic navigation and shopping cart capabilities to mark items for purchase. Upon checkout, the Online Store will calculate a total for the order, including shipping and handling charges and the associated taxes, as applicable.&nbsp; The following payment options should be provided:</span></p><p class="rally-rte-class-03221dadb"><span class="rally-rte-class-0b1c8cea2"><img src="https://lh5.googleusercontent.com/R-2ZX8gA5GTrG8A2OzIRpBjUFx6_RNRSVoZQxOvo7gSmeP4Wjp6eIkWdOcv0s05-zf6Hm_L4OEfJLpvmjqiEUdC_b-bW-Xo9JkCqTFdYywCJvEueazAj3EfDrTxXUdGCpcAQeHM" width="500px;" height="138px;" class="CToWUd rally-rte-class-047830fe9" /></span></p><p class="rally-rte-class-03cb47fb2">High-level functionality is expected to include:</p><ul><li>Intake items from the Online Store Search &amp; Browse functions</li><li>Viewing Recent Purchases to encourage repeat purchases</li><li>Persisting the Shopping Cart content between sessions</li><li>Clear calls to action for Purchasing Items</li><li>Reasonable scalability for initial roll-out and early growth (TBD)</li></ul> | #ee6c19 |  | FALSE | 8 | 8 | L | Discover | 20 | Test
Priority shipping | Short Term Growth | Fulfillment Team | pam@acme.com | Integrate in-store and online experience | R2 | 2018-01-15 | 2018-02-12 |  | #f9a814 |  | FALSE | 7 | 5 | L | Develop | 21 | Test
Rearchitect User Management | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R2 | 2018-01-18 | 2018-02-18 |  | #4a1d7e |  | FALSE | 4 | 5 | S | Discover | 22 | Test
Creation of cart | Short Term Growth | Shopping Team | peter@acme.com | Personalized online shopping experience | R2 | 2018-01-15 | 2018-02-24 |  | #107c1e |  | FALSE | 1 | 0 | M | Develop | 23 | Test
Special Offers | Short Term Growth | Shopping Team | peter@acme.com | Personalized online shopping experience | R2 | 2018-01-24 | 2018-02-21 |  | #107c1e |  | FALSE | 3 | 14 | M | Develop | 24 | Test
Online refunds | Short Term Growth | Fulfillment Team | patricia@acme.com | Modernize customer service portal | R2 | 2017-12-31 | 2018-02-09 | see business case attached | #4a1d7e |  | FALSE | 6 | 6 | M | Develop | 25 | Test
Integrate with Paypal | Short Term Growth | Payment Team | patricia@acme.com | Re-build primary web app leverage API technology | R2 | 2018-01-09 | 2018-02-09 | see business case attached | #ee6c19 |  | FALSE | 3 | 6 | M | Develop | 26 | Test
Integrate with WePay | Strategic Growth | Payment Team | patricia@acme.com | Re-build primary web app leverage API technology | R2 | 2018-01-09 | 2018-02-09 | see business case attached | #ee6c19 |  | FALSE | 6 | 6 | M | Develop | 27 | Test
Refund management | Short Term Growth | Fulfillment Team | pam@acme.com | Modernize customer service portal | R2 | 2018-01-09 | 2018-02-09 | see business case attached | #4a1d7e |  | FALSE | 3 | 6 | M | Develop | 28 | Test
Auto social links | Short Term Growth | Shopping Team | peter@acme.com | Build read-write API for handling orders | R2 | 2018-04-29 | 2018-07-16 |  | #21a2e0 |  | FALSE | 3 | 3 | M | Discover | 29 | Test
Shopping preferences | Strategic Growth | Shopping Team | peter@acme.com | Personalized online shopping experience |  | 2018-01-09 | 2018-02-24 |  | #107c1e |  | FALSE | 5 | 0 | L | Develop | 30 | Test
Provide public API to support 3rd party integrations | Strategic Growth | API Team | peter@acme.com | Integrate social into shopping experience | R2 | 2018-02-03 | 2018-02-24 | <span style="color: rgb(0, 0, 0); font-family: arial, helvetica, sans-serif; font-size: 12px; font-style: normal; font-variant: normal; font-weight: normal; letter-spacing: normal; line-height: normal; orphans: auto; text-align: left; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; background-color: rgb(255, 255, 255); display: inline !important; float: none;">Allow 3rd party integrators to access our data.</span> | #848689 |  | FALSE | 3 | 3 | L | Discover | 31 | Test
Provide link to twitter so users can tweet about products they are researching. | Short Term Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R2 | 2018-01-07 | 2018-01-30 |  | #105cab |  | FALSE | 3 | 3 | M | Discover | 32 | Test
Suggest products purchased by friends | Strategic Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R2 | 2018-02-10 | 2018-02-24 |  | #105cab |  | FALSE | 1 | 5 | S | Discover | 33 | Test
Error checking of profiles | Strategic Growth | API Team | peter@acme.com | Build read-write API for handling orders | R2 | 2018-02-03 | 2018-06-16 | <span style="color: rgb(0, 0, 0); font-family: arial, helvetica, sans-serif; font-size: 12px; font-style: normal; font-variant: normal; font-weight: normal; letter-spacing: normal; line-height: normal; orphans: auto; text-align: left; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; background-color: rgb(255, 255, 255); display: inline !important; float: none;">Allow 3rd party integrators to access our data.</span> | #21a2e0 |  | FALSE | 3 | 3 | L | Discover | 34 | Test
Integrate with Amex Gateway | None | Payment Team | patricia@acme.com | Minimal online shopping site | R2 |  |  | see business case attached | #105cab |  | FALSE | 5 | 6 | S | Discover | 35 | Test
Backorder fulfillment | None | Fulfillment Team | pam@acme.com | Minimal online shopping site | R2 |  |  |  | #105cab | [6 empty] | 36 | Test
Integrate with coupon.com site to match *popular* items in shopping cart | Cost Savings | Payment Team | aaron@acme.com | Integrate social into shopping experience | R2 | 2017-12-31 | 2018-02-03 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #848689 |  | FALSE | 1 | 8 | XS | Discover | 37 | Test
Order purchase API | Strategic Growth | API Team | aaron@acme.com | Minimal online shopping site | R2 | 2017-12-31 | 2018-02-17 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #105cab |  | FALSE | 1 | 8 | L | Discover | 38 | Test
Security layer for read-write API | None | API Team | aaron@acme.com | Build read-write API for handling orders | R2 | 2018-01-30 | 2018-02-17 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #21a2e0 |  | FALSE | 1 | 8 | S | Discover | 39 | Test
#ERROR! | None | Consumer Site | [13 empty] | 40 | Test
API for Shipping | Strategic Growth | API Team | aaron@acme.com | Create a read-only API | R3 | [5 empty] | FALSE | 5 | 1 | L | Propose | 41 | Test
User Profile | Short Term Growth | Shopping Team | peter@acme.com | Personalized online shopping experience | R3 | 2018-02-25 | 2018-03-22 |  | #107c1e |  | FALSE | 2 | 7 | M | Discover | 42 | Test
Credit card error messaging | None | Payment Team | patricia@acme.com | Maintain legacy purchasing system | R3 |  |  |  | #df1a7b |  | FALSE | 5 | 5 | S | Propose | 43 | Test
Product Listings | Short Term Growth | Shopping Team | peter@acme.com | Re-build primary web app leverage API technology | R3 | 2018-03-27 | 2018-04-21 |  | #ee6c19 |  | FALSE | 7 | 10 | M | Propose | 44 | Test
Realtime chat support | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R3 | 2018-02-28 | 2018-04-09 |  | #4a1d7e |  | FALSE | 3 | 5 | S | Discover | 45 | Test
Implement Fraud Detection | Strategic Growth | Payment Team | patricia@acme.com | Re-build primary web app leverage API technology | R3 | 2018-03-09 | 2018-04-15 | see business case attached | #ee6c19 |  | FALSE | 5 | 6 | S | Develop | 46 | Test
Mobile shopping Cart | Cost Savings | Shopping Team | peter@acme.com | MV mobile online shopping site | R3 | 2018-05-07 | 2018-06-01 | <p class="rally-rte-class-03cb47fb2"><span class="rally-rte-class-04dd18d0f">Build a shopping cart module to select items for eventual purchase. Provide basic navigation and shopping cart capabilities to mark items for purchase. Upon checkout, the Online Store will calculate a total for the order, including shipping and handling charges and the associated taxes, as applicable.&nbsp; The following payment options should be provided:</span></p><p class="rally-rte-class-03221dadb"><span class="rally-rte-class-0b1c8cea2"><img src="https://lh5.googleusercontent.com/R-2ZX8gA5GTrG8A2OzIRpBjUFx6_RNRSVoZQxOvo7gSmeP4Wjp6eIkWdOcv0s05-zf6Hm_L4OEfJLpvmjqiEUdC_b-bW-Xo9JkCqTFdYywCJvEueazAj3EfDrTxXUdGCpcAQeHM" width="500px;" height="138px;" class="CToWUd rally-rte-class-047830fe9" /></span></p><p class="rally-rte-class-03cb47fb2">High-level functionality is expected to include:</p><ul><li>Intake items from the Online Store Search &amp; Browse functions</li><li>Viewing Recent Purchases to encourage repeat purchases</li><li>Persisting the Shopping Cart content between sessions</li><li>Clear calls to action for Purchasing Items</li><li>Reasonable scalability for initial roll-out and early growth (TBD)</li></ul> | #21a2e0 |  | FALSE | 3 | 8 | M | Develop | 47 | Test
Cross sell related products | Strategic Growth | Shopping Team | peter@acme.com | Build read-write API for handling orders | R1 | 2018-02-03 | 2018-02-17 |  | #21a2e0 |  | FALSE | 6 | 3 | M | Propose | 48 | Test |  |  |  | 50
Allow user to vote on products | Strategic Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R3 | 2018-01-14 | 2018-01-30 |  | #105cab |  | FALSE | 2 | 4 | L | Discover | 49 | Test
Support cash/check by mail | None | Payment Team | patricia@acme.com | Minimal online shopping site | R3 |  |  | see business case attached | #105cab |  | FALSE | 5 | 6 |  | Propose | 50 | Test
Duplcate order fulfillment | None | Fulfillment Team | pam@acme.com | Build read-write API for handling orders | R1 |  |  |  | #21a2e0 | [5 empty] | Discover | 51 | Test
Order history API | Strategic Growth | API Team | aaron@acme.com | Minimal online shopping site | R3 | 2018-01-14 | 2018-02-10 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #105cab |  | FALSE | 1 | 8 | M | Discover | 52 | Test
Add web services for API write and delete | Strategic Growth | API Team | aaron@acme.com | Provide customer service portal for pickup | R3 | 2018-04-25 | 2018-05-29 |  | #df1a7b |  | FALSE | 2 | 0 | S | Develop | 53 | Test
Support ability to attach case and email notification | Cost Savings | API Team | aaron@acme.com | Innovate and develop purchasing system | R3 | 2018-04-28 | 2018-06-04 |  | #ee6c19 |  | FALSE | 12 | 4 | M | Develop | 54 | Test
Modify profile sharing with popular platforms | Maintenance | Shopping Team | peter@acme.com | Build location awareness for handling orders | R3 | 2018-04-28 | 2018-05-17 |  | #4a1d7e |  | FALSE | 2 | 0 | M | Develop | 55 | Test
Add additional chat platforms | Strategic Growth | Fulfillment Team | aaron@acme.com | Provide customer service portal for pickup | R3 | 2018-04-25 | 2018-06-04 |  | #df1a7b |  | FALSE | 5 | 3 | M | Develop | 56 | Test
Eliminate batch process to notification | Strategic Growth | API Team | aaron@acme.com | Innovate social selling, buying, rating systems | R3 | 2018-02-03 | 2018-06-16 | All users should be able to easily login, logout, and safely store their relevant information with us<br /><br />Acceptance Criteria <ul> <li>Login requires username in email format and password</li> <li>One-click logout</li> <li>Logout provides link to login again</li> <li><b>Non-functional: https data transfer</b></li> <li><b>Non-functional: passwords stored encrypted in database</b></li> </ul> |  |  | FALSE | 6 | 20 | L | Develop | 57 | Test
Allow users to reset purchase history | Strategic Growth | Fulfillment Team | pam@acme.com | Build location awareness for handling orders | R3 | 2018-04-22 | 2018-06-13 |  | #4a1d7e |  | FALSE | 4 | 0 | L | Develop | 58 | Test
Allow users to dissassociate suggestions | Short Term Growth | Payment Team | patricia@acme.com | MV mobile online shopping site | R3 | 2018-04-22 | 2018-06-01 | see business case attached | #21a2e0 |  | FALSE | 6 | 6 | M | Develop | 59 | Test
Product suggestion settings | Strategic Growth | Fulfillment Team | peter@acme.com | Innovate social selling, buying, rating systems | R3 | 2018-02-10 | 2018-06-16 |  |  |  | FALSE | 1 | 5 | S | Discover | 60 | Test
Users can add likes to products | Strategic Growth | Fulfillment Team | peter@acme.com | Innovate social selling, buying, rating systems | R3 | 2018-02-03 | 2018-06-09 |  |  |  | FALSE | 6 | 3 | XS | Propose | 61 | Test
#ERROR! | None | Consumer Site | [13 empty] | 62 | Test
Single product purchase click | Short Term Growth | Shopping Team | peter@acme.com | MV mobile online shopping site | R4 | 2018-04-22 | 2018-07-16 |  | #21a2e0 |  | FALSE | 13 | 10 | M | Open Beta | 63 | Test
Share all customer reviews | Short Term Growth | Fulfillment Team | pam@acme.com | MV mobile online shopping site | R4 | 2018-05-01 | 2018-07-13 |  | #21a2e0 |  | FALSE | 6 | 1 | L | Done | 64 | Test
Revamp homepage to be mobile ready | Cost Savings | Shopping Team | peter@acme.com | MV mobile online shopping site | R4 | 2018-05-22 | 2018-07-31 |  | #21a2e0 |  | FALSE | 5 | 7 | L | Internal Release | 65 | Test
Purchase confirmation settings in profile | Strategic Growth | Shopping Team | peter@acme.com | MV mobile online shopping site | R4 | 2018-04-28 | 2018-07-22 |  | #21a2e0 |  | FALSE | 4 | 3 | XL | Done | 66 | Test
Track orders returned for credit | Strategic Growth | Fulfillment Team | pam@acme.com | MV mobile online shopping site | R4 | 2018-04-28 | 2018-07-22 |  | #21a2e0 | [5 empty] | Develop | 67 | Test
Search based on profile attributes | Short Term Growth | Shopping Team | peter@acme.com | MV mobile online shopping site | R4 | 2018-05-16 | 2018-07-13 |  | #21a2e0 |  | FALSE | 0 | 5 | M | Open Beta | 68 | Test
Order history available | Strategic Growth | Fulfillment Team | pam@acme.com | Build location awareness for handling orders | R4 | 2018-04-28 | 2018-07-22 |  | #4a1d7e |  | FALSE | 3 | 4 | M | Done | 69 | Test
Email integration (case, online chat, customer service) | Cost Savings | API Team | aaron@acme.com | Innovate and develop purchasing system | R4 | 2018-04-22 | 2018-06-16 |  | #ee6c19 |  | FALSE | 1 | 9 | M | Develop | 70 | Test
Support case support with text verification | Cost Savings | API Team | aaron@acme.com | Innovate and develop purchasing system | R4 | 2018-05-01 | 2018-05-17 |  | #ee6c19 |  | FALSE | 3 | 5 | M | Develop | 71 | Test
AnyMethod payments | Cost Savings | Payment Team | patricia@acme.com | MV mobile online shopping site | R4 | 2018-05-01 | 2018-06-07 | see business case attached | #21a2e0 |  | FALSE | 3 | 6 | L | Validate | 72 | Test
Identify other items to purchase | Cost Savings | Shopping Team | peter@acme.com | MV mobile online shopping site | R4 | 2018-04-22 | 2018-06-10 | <p class="rally-rte-class-03cb47fb2"><span class="rally-rte-class-04dd18d0f">Build a shopping cart module to select items for eventual purchase. Provide basic navigation and shopping cart capabilities to mark items for purchase. Upon checkout, the Online Store will calculate a total for the order, including shipping and handling charges and the associated taxes, as applicable.&nbsp; The following payment options should be provided:</span></p><p class="rally-rte-class-03221dadb"><span class="rally-rte-class-0b1c8cea2"><img src="https://lh5.googleusercontent.com/R-2ZX8gA5GTrG8A2OzIRpBjUFx6_RNRSVoZQxOvo7gSmeP4Wjp6eIkWdOcv0s05-zf6Hm_L4OEfJLpvmjqiEUdC_b-bW-Xo9JkCqTFdYywCJvEueazAj3EfDrTxXUdGCpcAQeHM" width="500px;" height="138px;" class="CToWUd rally-rte-class-047830fe9" /></span></p><p class="rally-rte-class-03cb47fb2">High-level functionality is expected to include:</p><ul><li>Intake items from the Online Store Search &amp; Browse functions</li><li>Viewing Recent Purchases to encourage repeat purchases</li><li>Persisting the Shopping Cart content between sessions</li><li>Clear calls to action for Purchasing Items</li><li>Reasonable scalability for initial roll-out and early growth (TBD)</li></ul> | #21a2e0 |  | FALSE | 8 | 8 | L | Discover | 73 | Test
Provide cost options for shipping methods | Short Term Growth | Fulfillment Team | pam@acme.com | MV mobile online shopping site | R4 | 2018-05-07 | 2018-06-04 |  | #21a2e0 |  | FALSE | 7 | 5 | L | Develop | 74 | Test
Order Status 4.0 | Strategic Growth | Shopping Team | peter@acme.com | Provide customer service portal for pickup | R4 | 2018-04-28 | 2018-06-01 |  | #df1a7b |  | FALSE | 4 | 7 | M | Develop | 75 | Test
Integrate User Management with Profile Management | Strategic Growth | API Team | aaron@acme.com | Provide customer service portal for pickup | R4 | 2018-05-10 | 2018-06-10 |  | #df1a7b |  | FALSE | 4 | 5 | S | Discover | 76 | Test
Render product images on mobile platforms | Short Term Growth | Payment Team | patricia@acme.com | MV mobile online shopping site | R4 | 2018-05-01 | 2018-06-01 | see business case attached | #21a2e0 |  | FALSE | 3 | 6 | M | Develop | 77 | Test
Allow users to save carts | Strategic Growth | Payment Team | patricia@acme.com | MV mobile online shopping site | R4 | 2018-05-01 | 2018-06-01 | see business case attached | #21a2e0 |  | FALSE | 6 | 6 | M | Develop | 78 | Test
Credit refunds to new purchases | Short Term Growth | Fulfillment Team | pam@acme.com | MV mobile online shopping site | R4 | 2018-05-01 | 2018-06-01 | see business case attached | #21a2e0 |  | FALSE | 3 | 6 | M | Develop | 79 | Test
Implement Open API | Strategic Growth | API Team | aaron@acme.com | Ensure Agility Redefine how work is planned, achieve speed to value | R4 |  |  |  | #105cab |  | FALSE | 5 | 1 | L | Propose | 80 | Test
Credit card processing with realtime feedback | None | Payment Team | patricia@acme.com | MV mobile online shopping site | R4 |  |  |  | #21a2e0 |  | FALSE | 5 | 5 | S | Propose | 81 | Test
Support portal on web | Strategic Growth | API Team | aaron@acme.com | Provide customer service portal for pickup | R4 | 2018-04-25 | 2018-06-04 |  | #df1a7b |  | FALSE | 3 | 5 | S | Discover | 82 | Test
Pickup at local depot | Strategic Growth | Payment Team | patricia@acme.com | MV mobile online shopping site | R4 | 2018-05-04 | 2018-06-10 | see business case attached | #21a2e0 |  | FALSE | 5 | 6 | XL | Develop | 83 | Test
re-establish logins every 60 days | Strategic Growth | API Team | aaron@acme.com | Embed Security designed from the outside it. | R4 | 2018-05-06 | 2018-06-02 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #107c1e |  | FALSE | 1 | 8 | M | Discover | 84 | Test
Users get authentication codes for API | None | API Team | aaron@acme.com | Embed Security designed from the outside it. | R4 | 2018-05-22 | 2018-06-09 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #107c1e |  | FALSE | 1 | 8 | S | Discover | 85 | Test
#ERROR! | None | Consumer Site | [13 empty] | 86 | Test
Provide re-purchase options | Cost Savings | API Team | aaron@acme.com | Innovate social selling, buying, rating systems |  | 2018-04-22 | 2018-05-26 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> |  |  | FALSE | 1 | 8 | L | Discover | 87 | Test
Login with text codes | Strategic Growth | API Team | aaron@acme.com | Embed Security designed from the outside it. |  | 2018-04-22 | 2018-06-09 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> | #107c1e |  | FALSE | 1 | 8 | L | Discover | 88 | Test
Allow voting up / down of product selections | Strategic Growth | Shopping Team | peter@acme.com | Innovate social selling, buying, rating systems |  | 2018-05-06 | 2018-07-16 |  |  |  | FALSE | 2 | 4 | L | Discover | 89 | Test
Open integration platform | None | Payment Team | patricia@acme.com | MV mobile online shopping site |  |  |  | see business case attached | #21a2e0 |  | FALSE | 5 | 6 | XL | Discover | 90 | Test
Allow user accounts to sell products | None | Payment Team | patricia@acme.com | MV mobile online shopping site |  |  |  | see business case attached | #21a2e0 |  | FALSE | 5 | 6 |  | Propose | 91 | Test
Sell by rankings | None | Fulfillment Team | pam@acme.com | MV mobile online shopping site |  |  |  |  | #21a2e0 | [6 empty] | 92 | Test
Identify and auto notify duplicate orders | None | Fulfillment Team | pam@acme.com | MV mobile online shopping site |  |  |  |  | #21a2e0 |  |  |  |  | L | Discover | 93 | Test
Allow customization of Profiles | Short Term Growth | Shopping Team | peter@acme.com | MV mobile online shopping site |  | 2018-04-22 | 2018-05-17 |  | #21a2e0 |  | FALSE | 2 | 7 | M | Discover | 94 | Test
Build "As-U-Shop" cart | Short Term Growth | Shopping Team | peter@acme.com | Build location awareness for handling orders |  | 2018-05-07 | 2018-06-16 |  | #4a1d7e |  | FALSE | 1 | 0 | M | Develop | 95 | Test
Simplify special orders | Short Term Growth | Shopping Team | peter@acme.com | Build location awareness for handling orders |  | 2018-05-16 | 2018-06-13 |  | #4a1d7e |  | FALSE | 3 | 14 | M | Develop | 96 | Test
Wish list | Short Term Growth | Shopping Team | peter@acme.com | MV mobile online shopping site |  | 2018-05-22 | 2018-06-16 |  | #21a2e0 |  | FALSE | 7 | 10 | M | Propose | 97 | Test
Profile preferences | Strategic Growth | Shopping Team | peter@acme.com | Build location awareness for handling orders |  | 2018-05-01 | 2018-06-16 |  | #4a1d7e |  | FALSE | 5 | 0 | L | Develop | 98 | Test
<hr style="height:10px;border:none;color:#ff0000;background-color:#ff0000;" /> | None | Consumer Site | [13 empty] | 99 | Test
#ERROR! | None | Consumer Site | [13 empty] | 100 | Test