## iteration.csv
Project | Name | StartDate | EndDate | PlannedVelocity | State | Theme | Notes | dataset
Analytics Team | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
API Team | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Consumer Site | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Fulfillment Team | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 12 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Online Store | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Payment Team | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Reseller Portal Team | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Reseller Site | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 10 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Shopping Team | Iteration 1 | 2017-09-11 09:35 | 2017-09-24 09:35 | 12 | Accepted | <ul><li>Be able to Log-in and Log-off</li><li>Security implemented</li></ul> |  | Summer
Analytics Team | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
API Team | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Consumer Site | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Fulfillment Team | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 12 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Online Store | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Payment Team | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Reseller Portal Team | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Reseller Site | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 10 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Shopping Team | Iteration 2 | 2017-09-25 09:35 | 2017-10-08 09:35 | 12 | Accepted | <ul><li>Shop for Items</li><li>Start Shipping functionality</li><li>Purchase your Items - Part 1</li></ul> |  | Summer
Analytics Team | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
API Team | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Consumer Site | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Fulfillment Team | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Online Store | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Payment Team | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Reseller Portal Team | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Reseller Site | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 12 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Shopping Team | Iteration 3 | 2017-10-09 09:35 | 2017-10-22 09:35 | 25 | Accepted | <ul><li>Be able to Ship an Order</li><li>Provide Credit Card support</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Gigi, <b>Scribe:</b> Sara</i>)<br /><br /><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul><li>Align standup start time with Sara's bus schedule.</li><li>Improve test coverage from 8% to 12%</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><br /> <ul> <li><i>None.</i></li> </ul> | Summer
Analytics Team | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
API Team | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Consumer Site | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Fulfillment Team | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Online Store | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Payment Team | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Reseller Portal Team | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Reseller Site | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 20 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Shopping Team | Iteration 4 | 2017-10-23 09:35 | 2017-11-05 09:35 | 25 | Accepted | <ul><li>Hardening for ML</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> Paul, <b>Scribe:</b> John</i>)<br /><br /> <b>Appreciations</b><ul><li>Sara appreciated Susan for pair programming.</li><li>David appreciated John for attending standsups on-time.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i><ul> <li>Improve test coverage from 12% to 20%</li> <li>Add standup question 'What new information have we learned?'</li> <li>Learn Ruby as primary scripting lang</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Work with QA to move a team member into the dev area</li> <li>Request Agile Coach for Agile tune up</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>None.</li> </ul> | Summer
Analytics Team | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
API Team | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Consumer Site | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Fulfillment Team | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 20 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Online Store | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Payment Team | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b> <ul> <li>Paul appreciated John for helping with Ruby.</li> </ul> <b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li> <li>Switch from cruise control to jenkins.</li> </ul> <b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i> <ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul> <b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i> <ul> <li>Not enough professional development offered to team</li> <li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Reseller Portal Team | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Reseller Site | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 18 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Shopping Team | Iteration 5 | 2017-11-06 09:35 | 2017-11-19 09:35 | 40 | Accepted | <ul><li>Internationalize</li></ul> | <u>Retrospective Notes</u>&nbsp;&nbsp;(<i><b>Facilitator:</b> David, <b>Scribe:</b> Paul</i>)<br /><br /><b>Appreciations</b><ul><li>Paul appreciated John for helping with Ruby.</li></ul><b>Team Control</b>&nbsp;&nbsp;<i>(Create our own reality)</i> <ul> <li>Rule of 3: Three people (PO/Dev/QA) need to be involved in any conversation about requirements.</li><li>Switch from cruise control to jenkins.</li> </ul><b>Team Influence</b>&nbsp;&nbsp;<i>(ASK's of the organization)</i><ul> <li>Can we move off of clearcase?</li> <li>Request User Story writing workshop.</li> </ul><b>Soup</b>&nbsp;&nbsp;<i>(Everything else)</i><ul> <li>Not enough professional development offered to team</li><li>Weather in California is too nice to work indoors.</li> </ul> | Summer
Analytics Team | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
API Team | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Consumer Site | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Fulfillment Team | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Online Store | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Payment Team | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Platform | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Reseller Portal Team | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Reseller Site | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 20 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Shopping Team | Iteration 6 | 2017-11-20 09:35 | 2017-12-03 09:35 | 40 | Committed | <ul><li>Be able to complete the purchase</li><li>Be able to search for an item</li><li>Spikes</li></ul> |  | Summer
Analytics Team | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
API Team | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Consumer Site | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Fulfillment Team | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Online Store | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Payment Team | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Platform | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Reseller Portal Team | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Reseller Site | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 22 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Shopping Team | Iteration 7 | 2017-12-04 09:35 | 2017-12-17 09:35 | 40 | Planning | <ul><li>Hardening for OM</li></ul> |  | Summer
Analytics Team | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
API Team | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Consumer Site | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Fulfillment Team | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Online Store | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Payment Team | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Platform | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Reseller Portal Team | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Reseller Site | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Shopping Team | Iteration 8 | 2017-12-18 09:35 | 2017-12-31 09:35 | 22 | Planning | <ul><li>Similar Products</li></ul> |  | Summer
Analytics Team | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
API Team | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Consumer Site | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Fulfillment Team | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Online Store | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Payment Team | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Platform | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Reseller Portal Team | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Reseller Site | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Shopping Team | Iteration 9 | 2018-01-01 09:35 | 2018-01-14 09:35 | 20 | Planning | <ul><li>Personal Shopping Assistant</li></ul> |  | Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Summer
Analytics Team | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
API Team | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Consumer Site | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Fulfillment Team | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Online Store | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Payment Team | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Platform | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Reseller Portal Team | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Reseller Site | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Custom Ordering</li></ul>
Shopping Team | Iteration 10 | 2018-01-15 09:35 | 2018-01-28 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Analytics Team | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
API Team | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Consumer Site | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Fulfillment Team | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Online Store | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Payment Team | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Platform | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Reseller Portal Team | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Reseller Site | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Shopping Team | Iteration 11 | 2018-01-29 09:35 | 2018-02-11 09:35 | 20 | Planning | <ul><li>Enhanced notifications</li></ul>
Analytics Team | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
API Team | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Consumer Site | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Fulfillment Team | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Online Store | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Payment Team | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Platform | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Reseller Portal Team | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Reseller Site | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Shopping Team | Iteration 12 | 2018-02-12 09:35 | 2018-02-25 09:35 | 20 | Planning | <ul><li>Order Experience 2.0</li></ul>
Medical Records App | Iteration 4 - New Patients | 2017-11-20 09:35 | 2017-12-03 09:35 | 8 | Committed | New patients
Medical Records App | Iteration 5 - User Administration | 2017-12-04 09:35 | 2017-12-17 09:35 | 8 | Planning | User administration