## features.csv
Name | InvestmentCategory | Project | Owner | Parent | Release | PlannedStartDate | PlannedEndDate | Description | DisplayColor | Notes | Ready | RiskScore | ValueScore | PreliminaryEstimate | State | listing_order
Shopping Cart | Cost Savings | Shopping Team | peter@acme.com | Minimal online shopping site | R2 | 2017-08-11 10:59 | 2017-09-05 10:59 | <p class="rally-rte-class-03cb47fb2"><span class="rally-rte-class-04dd18d0f">Build a shopping cart module to select items for eventual purchase. Provide basic navigation and shopping cart capabilities to mark items for purchase. Upon checkout, the Online Store will calculate a total for the order, including shipping and handling charges and the associated taxes, as applicable.&nbsp; The following payment options should be provided:</span></p><p class="rally-rte-class-03221dadb"><span class="rally-rte-class-0b1c8cea2"><img src="https://lh5.googleusercontent.com/R-2ZX8gA5GTrG8A2OzIRpBjUFx6_RNRSVoZQxOvo7gSmeP4Wjp6eIkWdOcv0s05-zf6Hm_L4OEfJLpvmjqiEUdC_b-bW-Xo9JkCqTFdYywCJvEueazAj3EfDrTxXUdGCpcAQeHM" width="500px;" height="138px;" class="CToWUd rally-rte-class-047830fe9" /></span></p><p class="rally-rte-class-03cb47fb2">High-level functionality is expected to include:</p><ul><li>Intake items from the Online Store Search &amp; Browse functions</li><li>Viewing Recent Purchases to encourage repeat purchases</li><li>Persisting the Shopping Cart content between sessions</li><li>Clear calls to action for Purchasing Items</li><li>Reasonable scalability for initial roll-out and early growth (TBD)</li></ul> |  |  | FALSE | 3 | 8 | M | Develop | 1
Support write API | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R2 | 2017-07-30 10:59 | 2017-09-02 10:59 |  |  |  | FALSE | 2 | 0 | S | Develop | 2
Extended Email-to-case integration | Cost Savings | API Team | aaron@acme.com | Maintain legacy purchasing system | R2 | 2017-08-02 10:59 | 2017-09-08 10:59 |  |  |  | FALSE | 12 | 4 | M | Develop | 3
Saving profile | Maintenance | Shopping Team | peter@acme.com | Personalized online shopping experience | R2 | 2017-08-02 10:59 | 2017-08-21 10:59 |  |  |  | FALSE | 2 | 0 | M | Develop | 4
Online chat support | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R2 | 2017-07-30 10:59 | 2017-09-08 10:59 |  |  |  | FALSE | 5 | 3 | M | Develop | 5
Realtime notifications | Strategic Growth | API Team | aaron@acme.com | Integrate social into shopping experience | R2 | 2017-08-30 10:59 | 2017-09-20 10:59 | All users should be able to easily login, logout, and safely store their relevant information with us<br /><br />Acceptance Criteria <ul> <li>Login requires username in email format and password</li> <li>One-click logout</li> <li>Logout provides link to login again</li> <li><b>Non-functional: https data transfer</b></li> <li><b>Non-functional: passwords stored encrypted in database</b></li> </ul> |  |  | FALSE | 6 | 20 | L | Develop | 6
Email-to-case integration | Cost Savings | API Team | aaron@acme.com | Maintain legacy purchasing system | R2 | 2017-07-27 10:59 | 2017-09-20 10:59 |  |  |  | FALSE | 1 | 9 | M | Develop | 7
Outbound SMS messages for support case updates | Cost Savings | API Team | aaron@acme.com | Maintain legacy purchasing system | R2 | 2017-08-05 10:59 | 2017-08-21 10:59 |  |  |  | FALSE | 3 | 5 | M | Develop | 8
Credit card payments | Cost Savings | Payment Team | patricia@acme.com | Minimal online shopping site | R2 | 2017-08-05 10:59 | 2017-09-11 10:59 | see business case attached |  |  | FALSE | 3 | 6 | L | Validate | 9
Purchase path | Cost Savings | Shopping Team | peter@acme.com | Minimal online shopping site | R2 | 2017-07-27 10:59 | 2017-09-14 10:59 | <p class="rally-rte-class-03cb47fb2"><span class="rally-rte-class-04dd18d0f">Build a shopping cart module to select items for eventual purchase. Provide basic navigation and shopping cart capabilities to mark items for purchase. Upon checkout, the Online Store will calculate a total for the order, including shipping and handling charges and the associated taxes, as applicable.&nbsp; The following payment options should be provided:</span></p><p class="rally-rte-class-03221dadb"><span class="rally-rte-class-0b1c8cea2"><img src="https://lh5.googleusercontent.com/R-2ZX8gA5GTrG8A2OzIRpBjUFx6_RNRSVoZQxOvo7gSmeP4Wjp6eIkWdOcv0s05-zf6Hm_L4OEfJLpvmjqiEUdC_b-bW-Xo9JkCqTFdYywCJvEueazAj3EfDrTxXUdGCpcAQeHM" width="500px;" height="138px;" class="CToWUd rally-rte-class-047830fe9" /></span></p><p class="rally-rte-class-03cb47fb2">High-level functionality is expected to include:</p><ul><li>Intake items from the Online Store Search &amp; Browse functions</li><li>Viewing Recent Purchases to encourage repeat purchases</li><li>Persisting the Shopping Cart content between sessions</li><li>Clear calls to action for Purchasing Items</li><li>Reasonable scalability for initial roll-out and early growth (TBD)</li></ul> |  |  | FALSE | 8 | 8 | L | Discover | 10
Priority shipping | Short Term Growth | Fulfillment Team | pam@acme.com | Minimal online shopping site | R2 | 2017-08-11 10:59 | 2017-09-08 10:59 |  |  |  | FALSE | 7 | 5 | L | Develop | 11
Order Status 2.0 | Strategic Growth | Shopping Team | peter@acme.com | Modernize customer service portal | R2 | 2017-08-02 10:59 | 2017-09-05 10:59 |  |  |  | FALSE | 4 | 7 | M | Develop | 12
Rearchitect User Management | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R2 | 2017-08-14 10:59 | 2017-09-14 10:59 |  |  |  | FALSE | 4 | 5 | S | Discover | 13
Creation of cart | Short Term Growth | Shopping Team | peter@acme.com | Personalized online shopping experience | R2 | 2017-08-11 10:59 | 2017-09-20 10:59 |  |  |  | FALSE | 1 | 0 | M | Develop | 14
Special Offers | Short Term Growth | Shopping Team | peter@acme.com | Personalized online shopping experience | R2 | 2017-08-20 10:59 | 2017-09-17 10:59 |  |  |  | FALSE | 3 | 14 | M | Develop | 15
Shopping history | Strategic Growth | Fulfillment Team | pam@acme.com | Personalized online shopping experience | R2 | 2017-07-27 10:59 | 2017-09-17 10:59 |  |  |  | FALSE | 4 | 0 | L | Develop | 16
Online refunds | Short Term Growth | Payment Team | patricia@acme.com | Minimal online shopping site | R2 | 2017-07-27 10:59 | 2017-09-05 10:59 | see business case attached |  |  | FALSE | 6 | 6 | M | Develop | 17
Integrate with Paypal | Short Term Growth | Payment Team | patricia@acme.com | Minimal online shopping site | R2 | 2017-08-05 10:59 | 2017-09-05 10:59 | see business case attached |  |  | FALSE | 3 | 6 | M | Develop | 18
Integrate with WePay | Strategic Growth | Payment Team | patricia@acme.com | Minimal online shopping site | R2 | 2017-08-08 10:59 | 2017-09-20 10:59 | see business case attached |  |  | FALSE | 6 | 6 | M | Develop | 19
Refund management | Short Term Growth | Fulfillment Team | pam@acme.com | Minimal online shopping site | R2 | 2017-08-05 10:59 | 2017-09-05 10:59 | see business case attached |  |  | FALSE | 3 | 6 | M | Develop | 20
#ERROR! | None | Consumer Site | [13 empty] | 21
API for Shipping | Strategic Growth | API Team | aaron@acme.com | Create a read-only API | R3 | [5 empty] | FALSE | 5 | 1 | L | Propose | 22
User Profile | Short Term Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R3 | 2017-09-21 10:59 | 2017-10-16 10:59 |  |  |  | FALSE | 2 | 7 | M | Discover | 23
Credit card error messaging | None | Payment Team | patricia@acme.com | Minimal online shopping site | R3 | [5 empty] | FALSE | 5 | 5 | S | Propose | 24
Product Listings | Short Term Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R3 | 2017-10-21 10:59 | 2017-11-15 10:59 |  |  |  | FALSE | 7 | 10 | M | Propose | 25
Realtime chat support | Strategic Growth | API Team | aaron@acme.com | Modernize customer service portal | R3 | 2017-09-24 10:59 | 2017-11-03 10:59 |  |  |  | FALSE | 3 | 5 | S | Discover | 26
Shopping preferences | Strategic Growth | Shopping Team | peter@acme.com | Personalized online shopping experience | R2 | 2017-08-05 10:59 | 2017-09-20 10:59 |  |  |  | FALSE | 5 | 0 | L | Develop | 27
Implement Fraud Detection | Strategic Growth | Payment Team | patricia@acme.com | Minimal online shopping site | R3 | 2017-10-03 10:59 | 2017-11-09 10:59 | see business case attached |  |  | FALSE | 5 | 6 | XL | Develop | 28
#ERROR! | None | Consumer Site | [13 empty] | 29
Provide public API to support 3rd party integrations | Strategic Growth | API Team | peter@acme.com | Integrate social into shopping experience | R2 | 2017-08-30 10:59 | 2017-09-20 10:59 | <span style="color: rgb(0, 0, 0); font-family: arial, helvetica, sans-serif; font-size: 12px; font-style: normal; font-variant: normal; font-weight: normal; letter-spacing: normal; line-height: normal; orphans: auto; text-align: left; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; background-color: rgb(255, 255, 255); display: inline !important; float: none;">Allow 3rd party integrators to access our data.</span> |  |  | FALSE | 3 | 3 | L | Discover | 30
Provide link to twitter so users can tweet about products they are researching. | Short Term Growth | Shopping Team | peter@acme.com | Integrate social into shopping experience | R2 | 2017-08-03 10:59 | 2017-08-26 10:59 |  |  |  | FALSE | 3 | 3 | M | Discover | 31
Suggest products purchased by friends | Strategic Growth | Shopping Team | peter@acme.com | Integrate social into shopping experience | R2 | 2017-09-06 10:59 | 2017-09-20 10:59 |  |  |  | FALSE | 1 | 5 | XL | Discover | 32
Cross sell related products | Strategic Growth | Shopping Team | peter@acme.com | Integrate social into shopping experience | R2 | 2017-08-30 10:59 | 2017-09-13 10:59 |  |  |  | FALSE | 6 | 3 | M | Propose | 33
Allow user to vote on products | Strategic Growth | Shopping Team | peter@acme.com | Integrate social into shopping experience | R2 | 2017-08-10 10:59 | 2017-08-26 10:59 |  |  |  | FALSE | 2 | 4 | L | Discover | 34
Integrate with Amex Gateway | None | Payment Team | patricia@acme.com | Minimal online shopping site |  |  |  | see business case attached |  |  | FALSE | 5 | 6 | XL | Discover | 35
Support cash/check by mail | None | Payment Team | patricia@acme.com | Minimal online shopping site |  |  |  | see business case attached |  |  | FALSE | 5 | 6 |  | Propose | 36
Backorder fulfillment | None | Fulfillment Team | pam@acme.com | Minimal online shopping site | [11 empty] | 37
Duplcate order fulfillment | None | Fulfillment Team | pam@acme.com | Minimal online shopping site | [9 empty] | L | Discover | 38
Integrate with coupon.com site to match *popular* items in shopping cart | Cost Savings | API Team | aaron@acme.com | Integrate social into shopping experience | R2 | 2017-07-27 10:59 | 2017-08-30 10:59 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> |  |  | FALSE | 1 | 8 | L | Discover | 39
Order purchase API | Strategic Growth | API Team | aaron@acme.com | Build read-write API for handling orders | R2 | 2017-07-27 10:59 | 2017-09-13 10:59 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> |  |  | FALSE | 1 | 8 | L | Discover | 40
Order history API | Strategic Growth | API Team | aaron@acme.com | Build read-write API for handling orders | R2 | 2017-08-10 10:59 | 2017-09-06 10:59 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> |  |  | FALSE | 1 | 8 | M | Discover | 41
Security layer for read-write API | None | API Team | aaron@acme.com | Build read-write API for handling orders | R2 | 2017-08-26 10:59 | 2017-09-13 10:59 | <span class="rally-rte-class-0fdfe95d069988">Coupons.com is a premier supplier of coupons.</span> <div class="rally-rte-class-0355e3c0ca0a138"><br class="rally-rte-class-0655ac2f5dd0ba8" /></div> <div class="rally-rte-class-0355e3c0ca0a138">Match popular coupons with features in the users' cart.</div> |  |  | FALSE | 1 | 8 | S | Discover | 42
#ERROR! | None | Consumer Site | [13 empty] | 43
Purchase single product | Short Term Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R1 | 2017-06-01 10:59 | 2017-07-11 10:59 |  |  |  | FALSE | 13 | 10 | M | Open Beta | 44
Knowledgebase | Short Term Growth | Fulfillment Team | pam@acme.com | Minimal online shopping site | R1 | 2017-06-10 10:59 | 2017-07-08 10:59 |  |  |  | FALSE | 6 | 1 | L | Done | 45
Homepage | Cost Savings | Shopping Team | peter@acme.com | Minimal online shopping site | R1 | 2017-07-01 10:59 | 2017-07-26 10:59 |  |  |  | FALSE | 5 | 7 | L | Internal Release | 46
Product purchase confirmation | Strategic Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R1 | 2017-06-07 10:59 | 2017-07-17 10:59 |  |  |  | FALSE | 4 | 3 | XL | Done | 47
Returned shipments | Strategic Growth | Fulfillment Team | pam@acme.com | Minimal online shopping site | R1 | 2017-06-07 10:59 | 2017-07-17 10:59 | [7 empty] | Develop | 48
Search for products | Short Term Growth | Shopping Team | peter@acme.com | Minimal online shopping site | R1 | 2017-06-25 10:59 | 2017-07-08 10:59 |  |  |  | FALSE | 0 | 5 | M | Open Beta | 49
Archive packing slips | Strategic Growth | Fulfillment Team | pam@acme.com | Personalized online shopping experience | R1 | 2017-06-07 10:59 | 2017-07-17 10:59 |  |  |  | FALSE | 3 | 4 | M | Done | 50